## Tasks
Task ID | Executor | Date | Reminder Time | Task Description | Object | Section | Priority | Executor ID | Company | Reminder Sent | Reminder Sent Date | Reminder Read | Read Time | Reminder Count | Reminder Interval if No Report | Status | Comment | Report Date
ID900 | Артём Б | 2025-07-25 | 0.67639 | Монтаж опалубки | Коттедж 5 | А-12 | Средний | #REF! | #REF!
ID1 | Artem Boiko | 2025-07-27 | 0.70833 | Laying tiles 10 m2 | Apartment.1 | BA2 | High | 1099647350 | DDC | Yes | 27.07.2025, 19:34 | Yes | 26.07.2025, 08:33 | 13 | 00:01 | completed | No comment | 27.07.2025 16:06:07
ID2 | Artem Boiko | 2025-07-26 | 0.33333 | Checking window installation | Apartment.3 | BA3 | Low | 1099647350 | DDC | Yes | 29.07.2025, 00:33 | Yes | 26.07.2025, 08:33 | 2 | 64:00
ID3 | Artem Boiko | 2025-07-26 | 0.33333 | Laying laminate flooring | Apartment.2 | BA4 | Medium | 1099647350 | DDC | Yes | 26.07.2025, 08:33 | Yes | 26.07.2025, 08:33 | 1 |  | not completed | No material available | 26.07.2025 08:34:01
ID4 | AhmirZ | 27.07.2025 | 0.33333 | Laying laminate flooring | Apartment.1 | BA5 | High | 1688108831 | Elite Construction
ID5 | AhmirZ | 27.07.2025 | 0.33333 | Checking window installation | Apartment.2 | BA6 | Low | 1688108831 | Elite Construction
ID6 | Artem Boiko | 2025-07-27 | 0.125 | Checking window installation | Apartment.2 | BA7 | Medium | 1099647350 | DDC | Yes | 27.07.2025, 08:51 | Yes | 27.07.2025, 08:54 | 1 |  | completed | Everything is fine | 27.07.2025 08:51:12
ID7 | Lukas | 2025-07-27 | 0.125 | Installation task 1 | First property | No.46 | High | 366117835 | Zublin | Yes | 27.07.2025, 09:01 | Yes | 27.07.2025, 18:38 | 1
ID8 | Lukas | 2025-07-27 | 0.20833 | Send a message to check | First property | No.47 | Low | 366117835 | Zublin | Yes | 27.07.2025, 09:01 | Yes | 27.07.2025, 08:55 | 1
ID9 | Anna | 2025-07-27 | 0.64583 | Task 1 | HWB | Küche | Medium | 654958782 | KA | Yes | 27.07.2025, 16:04 | Yes | 27.07.2025, 16:05 | 1
ID10 | Anna | 2025-07-27 | 0.64583 | Task 2 | HWB | KZ | Medium | 654958782 | KA | Yes | 27.07.2025, 16:04 | Yes | 27.07.2025, 16:05 | 1 |  | completed | No comment | 27.07.2025 16:06:07
ID11 | Artem Boiko | 2025-07-27 | 0.64583 | Task 2 | HWB | KZ | Medium | 1099647350 | DDC | Yes | 29.07.2025, 13:44 | Yes | 27.07.2025, 17:54 | 12 | 00:01 | completed | Everything is fine | 27.07.2025 19:05:11
ID12 | Artem Boiko | 2025-07-27 | 0.72917 | Task 2 | HWB | KZ | Medium | 1099647350 | DDC | Yes | 29.07.2025, 13:43 | Yes | 27.07.2025, 18:10 | 10 | 00:01 | completed | Everything is fine | 27.07.2025 19:05:11
ID13 | Karpatys | 2025-07-27 | 0.7875 | Checking window installation | Second | 7 | Medium | 5827943653 | ConstructMode | Yes | 27.07.2025, 19:34 | Yes | 27.07.2025, 18:56 | 4 | 00:01 | partially | Everything is fine | 27.07.2025 18:56:58
ID14 | Karpatys | 2025-07-27 | 0.79167 | Checking window installation | Second | 8 | Low | 5827943653 | ConstructMode | Yes | 27.07.2025, 19:34 | Yes | 27.07.2025, 19:00 | 8 | 00:01 | completed | Everything is fine | 27.07.2025 19:05:11
ID15 | Karpatys | 2025-07-27 | 0.79167 | Checking window installation | Second | 9 | Low | 5827943653 | ConstructMode | Yes | 27.07.2025, 19:00 | Yes | 27.07.2025, 19:00 | 1 |  | completed | Everything is fine | 27.07.2025 19:03:16
ID16 | Yu | 28.07.2025 | 0.375 | Something important | Unique | 1 | High | 414016237 | Pi | Yes | 28.07.2025, 12:34 | Yes | 28.07.2025, 12:35 | 1 | 00:05 | completed | Is it case sensitive? | 28.07.2025 12:36:42
ID17 | Artem Boiko | 2025-07-28 | 0.4375 | Something important | Unique | 1 | High | 1099647350 | DDC | Yes | 28.07.2025, 12:36 |  |  | 1 |  | completed | Everything is fine | 28.07.2025 12:38:22
ID18 | Albert | 2025-07-28 | 0.58333 | Something important | Unique | 1 | High | 168401845 | BuildIn | Yes | 28.07.2025, 14:12 |  |  | 2 | 00:01 | completed | Everything is fine | 28.07.2025 14:12:14
ID19 | Albert | 2025-07-28 | 0.58333 | Something important | Unique | 1 | Low | 168401845 | BuildIn | Yes | 28.07.2025, 14:12 |  |  | 2 | 00:01 | completed | Everything is fine | 28.07.2025 14:12:42
ID20 | AhmirZ | 2025-07-28 | 0.61736 | Laying tiles 10 m2 | Apartment.1 | BA4 | Low | 1688108831 | Elite Construction | Yes | 28.07.2025, 15:05 | Yes | 28.07.2025, 15:05 | 2 | 00:01 | completed | Everything is fine | 28.07.2025 15:06:28
ID21 | AhmirZ | 2025-07-28 | 0.61736 | Checking window installation | Apartment.3 | BA5 | Low | 1688108831 | Elite Construction | Yes | 28.07.2025, 15:04 | Yes | 28.07.2025, 15:05 | 1 | 00:01 | completed | Everything is fine | 28.07.2025 15:05:20
ID22 | Artem Boiko | 2025-07-28 | 0.41667 | Checking window installation | Apartment.2 | BA6 | High | 1099647350 | DDC | Yes | 28.07.2025, 15:58 |  |  | 1 |  | completed | Everything is fine | 28.07.2025 16:01:23
ID23 | Artem Boiko | 2025-07-28 | 0.47917 | Checking window installation | Apartment 2 | BA6 | High | 1099647350 | DDC | Yes | 28.07.2025, 15:58 |  |  | 1 |  | completed | Everything is fine | 28.07.2025 16:01:20
ID24 | John Jr. Doe | 2025-07-29 | 0.35417 | Checking window installation | Apartment 2 | BA6 | High | 1099647350 | BuildCorp | Yes | 29.07.2025, 14:22 | Yes | 28.07.2025, 15:05 | 20 | 00:01 | completed | Everything is fine | 2025-07-29 11:29
ID25 | John Jr. Doe | 2025-07-29 | 0.083333 | Checking window installation | Apartment 2 | BA6 | High | 1099647350 | BuildCorp | Yes | 28.07.2025, 15:58 | Yes | 28.07.2025, 15:05 | 1 |  | completed | Everything is fine | 2025-07-29 11:29
ID26 | Norbert Paul | 2025-07-29 | 0.29167 | Checking window installation | Apartment 2 | BA6 | High | 1099647350 | BuildCorp2 | Yes |  | Yes | 29.07.2025, 13:24 | 1 | 00:01 | completed | Everything is fine | 2025-07-29 11:29
ID27 | John Doe Jr3 | 2025-07-29 | 0.54167 | Task 2 | HWB | KZ | High | 1099647350 | BuildCorp | Yes | 29.07.2025, 13:20 | Yes | 29.07.2025, 13:24 | 4 | 00:01 | completed | Everything is fine | 2025-07-29 13:21
ID28 | John Doe Jr3 | 2025-07-29 | 0.45833 | Laying laminate flooring | Apartment.2 | BA4 | Medium | 1099647350 | BuildCorp | Yes | 29.07.2025, 13:24 | Yes | 29.07.2025, 13:24 | 1 |  | completed | Everything is fine | 2025-07-29 13:25
ID29 | John Doe Jr3 | 2025-07-29 | 0.45833 | Laying tiles 10 m2 | Apartment.1 | BA2 | Low | 1099647350 | BuildCorp | Yes | 29.07.2025, 13:24 | Yes | 29.07.2025, 13:24 | 1 |  | completed | Everything is fine | 2025-07-29 13:25
ID30

## Photo Reports
Report ID | Executor | Report Type | Reminder Date | Reminder Time | Executor ID | Company | Reminder Sent | Reminder Sent Date | Reminder Read | Read Time | Reminder Count | Reminder Interval if No Report | Report Received Time | Document Type | File Name | File URL | Comment | File Count | Processing Status | GPS Coordinates | Report Date
| Artem Boiko | Number of workers on the construction site | 2025-07-24 | 0.67639 | 1099647350 | DDC
ID1 | Artem Boiko | Volume of construction work completed | 2025-07-27 | 0.4375 | 1099647350 | DDC | Yes | 27.07.2025, 17:39 | Yes | 27.07.2025, 17:27 | 5 | 00:01 | 27.07.2025, 17:39:29 | Пришли фото квартиры | 1099647350_ID1_570_1753637969361.jpg | https://drive.google.com/file/d/1-IGayAOyvycNrtJpRMz_cHjtvaJmapYo/view?usp=drivesdk | gf | 1 | File uploaded to Drive |  | 27.07.2025
ID2 | Artem Boiko | Photos of the general work log | 2025-07-26 | 0.33333 | 1099647350 | DDC | Yes | 26.07.2025, 08:38 | Yes | 26.07.2025, 08:38 | 1 | 64:00 | 26.07.2025, 08:39:48 | Количество рабочих на строительной площадке | 1099647350_ID2_324_1753519188792.jpg | https://drive.google.com/file/d/1EfYb2wENqdM6BIlOxfb3XEeenlPwzfFi/view?usp=drivesdk | nothing | 1 | File uploaded to Drive |  | 26.07.2025
ID3 | AhmirZ | Photos of the welding log | 2025-07-26 | 0.33333 | 1688108831 | Elite Construction | Yes | 26.07.2025, 08:38 | Yes | 26.07.2025, 08:38 | 1 |  | 26.07.2025, 08:40:03 | Фотографии журнала бетонных работ | 1099647350_ID3_326_1753519203228.jpg | https://drive.google.com/file/d/1Z_FIB8VbauKVywYhv1XaYp4Bcknm8g7V/view?usp=drivesdk | everything | 1 | File uploaded to Drive |  | 26.07.2025
ID4 | AhmirZ | Photos of the construction equipment log (machine hours) | 27.07.2025 | 0.33333 | 1688108831 | Elite Construction | Yes | 27.07.2025, 09:03 | Yes | 27.07.2025, 09:03 | 1 |  | 27.07.2025, 09:04:58 | Количество рабочих на строительной площадке | 1688108831_ID4_511_1753607098917.jpg | https://drive.google.com/file/d/1DZcGiwXWkOeog16EV6mIcKtWIdZILAj6/view?usp=drivesdk |  | 1 | File uploaded to Drive |  | 27.07.2025
ID5 | Anna | Photos of the welding log | 2025-07-27 | 0.625 | 654958782 | KA | Yes | 27.07.2025, 16:11 |  |  | 1
ID6 | Artem Boiko | Photos of the concrete work log | 2025-07-27 | 0.66667 | 1099647350 | DDC | Yes | 27.07.2025, 17:57 | Yes | 27.07.2025, 17:55 | 3 | 00:01 | 27.07.2025, 17:57:18 | Объём выполненных строительных работ | 1099647350_ID6_582_1753639038900.jpg | https://drive.google.com/file/d/1B-T1u1YI3Eyz0EEZtiojISOWYJQeobUH/view?usp=drivesdk | ok | 1 | File uploaded to Drive | 51.300287, 10.504999 | 27.07.2025
ID7 | Karpatys | Photos of the general work log | 2025-07-27 | 0.80208 | 5827943653 | ConstructMode | Yes | 27.07.2025, 19:16 | Yes | 27.07.2025, 19:16 | 2 | 00:01 | 27.07.2025, 19:26:31 | Количество рабочих на строительной площадке | 5827943653_ID7_679_1753644391417.jpg | https://drive.google.com/file/d/1E_SdJR6jiwwk25dzu_0ZcZfei4mNdvBT/view?usp=drivesdk | Change status | 1 | File uploaded to Drive | -16.97274, 96.913065 | 27.07.2025
ID8 | Yu | Photos of the welding log | 28.07.2025 | 0.375 | 414016237 | Pi | Yes | 28.07.2025, 12:40 | Yes | 28.07.2025, 12:39 | 2 | 00:01 | 28.07.2025, 12:40:41 | Фотографии выполненных объёмов работ | 414016237_ID8_746_1753706441154.jpg | https://drive.google.com/file/d/1HH9_ErNElxbE-m7-EhGzlaFJBuYHafxB/view?usp=drivesdk |  | 1 | File uploaded to Drive |  | 28.07.2025
ID9 | Evan | Photos of the welding log | 2025-07-28 | 0.41667 | 366117835 | ESK | Yes | 28.07.2025, 14:13 | Yes | 28.07.2025, 14:14 | 1 | 00:01 | 28.07.2025, 14:14:04 | Фотографии журнала сварочных работ | 1099647350_ID9_18_1753712044799.jpg | https://drive.google.com/file/d/11JGWYverf_22XOzEv-Gy-LUegY6gFUNM/view?usp=drivesdk | sdfgdsfg | 1 | File uploaded to Drive |  | 28.07.2025
ID10 | Albert | Photos of the concrete work log | 2025-07-28 | 0.62986 | 168401845 | BuildIn | Yes | 28.07.2025, 15:12 | Yes | 28.07.2025, 15:10 | 5 | 00:01 | 28.07.2025, 16:17:40 | Количество рабочих на строительной площадке | 1688108831_ID10_105_1753719460613.jpg | https://drive.google.com/file/d/19klNcBT3zKusUb-C8KR9uh0JxKGEx5-8/view?usp=drivesdk |  | 1 | File uploaded to Drive | -39.695398, 95.587706 | 28.07.2025
ID11 | Albert | Photos of the construction equipment log (machine hours) | 2025-07-28 | 0.62986 | 168401845 | BuildIn | Yes | 28.07.2025, 15:10 | Yes | 28.07.2025, 15:10 | 2 | 00:02 | 28.07.2025, 15:11:51 | Объём выполненных строительных работ | 1688108831_ID11_89_1753715511019.jpg | https://drive.google.com/file/d/1irSwPfUCSeIIHGOUSvW56Udec6Q51eZt/view?usp=drivesdk | Everything is ok | 1 | File uploaded to Drive |  | 28.07.2025
ID12 | John Jr. Doe | Photos of the welding log | 2025-07-29 | 0.4375 | 1099647350 | BuildCorp | Yes | 28.07.2025, 15:12 | Yes | 28.07.2025, 15:10 | 1 | 00:01 | 2025-07-29 11:48 | Photos of the welding log | 1099647350_ID12_96_1753789661199.jpg | https://drive.google.com/file/d/1hEIfdwM3OfdbHAfZR3dPKF7-4qeCYVgi/view?usp=drivesdk | kommetn | 1 | File uploaded to Drive |  | 2025-07-29
ID13 | John Jr. Doe | Photos of the general work log | 2025-07-29 | 0.22917 | 1099647350 | BuildCorp | Yes | 29.07.2025, 13:44 | Yes | 28.07.2025, 15:10 | 4 | 00:01 | 2025-07-29 13:37 | Photos of the construction equipment log (machine hours) | 1099647350_ID14_159_1753796240566.jpg | https://drive.google.com/file/d/1ko6HKuWYZYWjg2QWBAidElK-arxJkoOT/view?usp=drivesdk | komment | 1 | File uploaded to Drive |  | 2025-07-29
ID14 | John Doe Jr3 | Photos of the construction equipment log (machine hours) | 2025-07-29 | 0.5 | 1099647350 | BuildCorp | Yes | 29.07.2025, 13:33 | Yes | 29.07.2025, 13:37 | 1 |  | 2025-07-29 13:37 | Photos of the construction equipment log (machine hours) | 1099647350_ID14_159_1753796240566.jpg | https://drive.google.com/file/d/1ko6HKuWYZYWjg2QWBAidElK-arxJkoOT/view?usp=drivesdk | komment | 1 | File uploaded to Drive | 51.300287, 10.504999 | 2025-07-29
ID15 | John Doe Jr3 | Photos of the concrete work log | 2025-07-29 | 0.29167 | 1099647350 | BuildCorp | Yes | 29.07.2025, 13:38 | Yes | 29.07.2025, 13:37 | 3 | 00:01 | 2025-07-29 14:57 | Photos of the concrete work log | 1099647350_ID15_198_1753801024021.jpg | https://drive.google.com/file/d/1osWQIw-_Jqmfqe0vmOFMqisd6Nhg879l/view?usp=drivesdk | Alles erledigt | 1 | File uploaded to Drive |  | 2025-07-29
ID16

## Users
Telegram ID | Registration Date | Executor Name | Telegram Name | Company
1099647350 | 26.07.2025, 08:29:57 | Artem Boiko | Artem Boiko | DDC
1688108831 | 27.07.2025, 08:17:01 | AhmirZ |  | Elite Construction
366117835 | 27.07.2025, 09:24:53 | Lukas |  | Zublin
654958782 | 27.07.2025, 16:01:14 | Anna |  | KA
5827943653 | 27.07.2025, 18:51:02 | Karpatys |  | ConstructMode
366117835 | 28.07.2025, 09:41:19 | Evan |  | ESK
414016237 | 28.07.2025, 11:34:14 | Yu |  | Pi
168401845 | 29.07.2025, 03:41:29 | Albert |  | BuildIn
1099647350 | 2025-07-29 10:57 | Artem Boiko | Artem Boiko | BuildCorp
1099647350 | 2025-07-29 10:59 | Artem Boiko | Artem Boiko | BuildCorp
1099647350 | 2025-07-29 11:00 | Artem Boiko | Artem Boiko | BuildCorp
1099647350 | 2025-07-29 11:00 | John Doe |  | BuildCorp
1099647350 | 2025-07-29 11:05 | John Jr. Doe | Artem Boiko | BuildCorp
1099647350 | 2025-07-29 11:35 | Norbert Paul | Artem Boiko | BuildCorp2
1099647350 | 2025-07-29 13:01 | John Doe Jr3 | Artem Boiko | BuildCorp

## Helper Lists
Indicator | Frequency | Description | Sending Time | Priority | Reminder Delay if No Response
Number of workers on the construction site | Daily | Recording the exact number of employees present at the site each day. | 0.020833 | High | 01:00
Volume of construction work completed | Daily | Indicating the amount or percentage of work completed in relation to the schedule. | 0.041667 | Medium | 02:00
Photos of completed work | Daily | Photographing key stages and areas where work has been completed or is ongoing. | 0.0625 | Low | 03:00
Photos of the general work log | Daily | Photographing completed pages of the general construction log with signatures. | 0.083333 |  | 04:00
Photos of the welding log | Daily | Photographs of current records of completed welding work. | 0.10417 |  | 05:00
Photos of the concrete work log | Daily | Photographs of records of concrete pouring, compositions, weather conditions, and tests. | 0.125 |  | 06:00
Photos of the construction equipment log (machine hours) | Daily | Documentation of equipment use and recording of machine hours worked. | 0.14583 |  | 07:00
Photos of primary accounting documents for materials received | As needed | Photographs of delivery notes, invoices, and other supporting documents for the delivery of materials. | 0.16667 |  | 08:00
|  |  | 0.1875 |  | 09:00
|  |  | 0.20833 |  | 1:000
|  |  | 0.22917 |  | 11:00
|  |  | 0.25 |  | 12:00
|  |  | 0.27083 |  | 13:00
|  |  | 0.29167 |  | 14:00
|  |  | 0.3125 |  | 15:00
|  |  | 0.33333 |  | 16:00
|  |  | 0.35417 |  | 17:00
|  |  | 0.375 |  | 18:00
|  |  | 0.39583 |  | 19:00
|  |  | 0.41667 |  | 2:000
|  |  | 0.4375 |  | 21:00
|  |  | 0.45833 |  | 22:00
|  |  | 0.47917 |  | 23:00
|  |  | 0.5 |  | 24:00
|  |  | 0.52083 |  | 25:00
|  |  | 0.54167 |  | 26:00
|  |  | 0.5625 |  | 27:00
|  |  | 0.58333 |  | 28:00
|  |  | 0.60417 |  | 29:00
|  |  | 0.625 |  | 3:000
|  |  | 0.64583 |  | 31:00
|  |  | 0.66667 |  | 32:00
|  |  | 0.6875 |  | 33:00
|  |  | 0.70833 |  | 34:00
|  |  | 0.72917 |  | 35:00
|  |  | 0.75 |  | 36:00
|  |  | 0.77083 |  | 37:00
|  |  | 0.79167 |  | 38:00
|  |  | 0.8125 |  | 39:00
|  |  | 0.83333 |  | 4:000
|  |  | 0.85417 |  | 41:00
|  |  | 0.875 |  | 42:00
|  |  | 0.89583 |  | 43:00
|  |  | 0.91667 |  | 44:00
|  |  | 0.9375 |  | 45:00
|  |  | 0.95833 |  | 46:00
|  |  | 0.97917 |  | 47:00
|  |  | 1 |  | 48:00
|  |  | write your time |  | 49:00
5:000
51:00
52:00
53:00
54:00
55:00
56:00
57:00
58:00
59:00
6:000
61:00
62:00
63:00
64:00
65:00
66:00
67:00
68:00
69:00
7:000
write your time